## Status Sheet
Sr no. | Feature additions / Modifications | Status | CRC Comment
1 | HMI changes for resolution/imperial to metric units | Done
2 | Changes in log timings, addition of columns(idle,spray,stall) to logs | Done
3 | Upload/Download Configuration Parameters using commands from App | In Progress
4 | Job Setup for Cloud- SCU Firmware changes including User Roles | Pending
5 | Data logging changes to accomodate additional data on XML files including firmware version list . Also be able to filter data based on date time for getting logs. | Pending
6 | Command to get Firmware version | Done( Need to be tested with Application )
7 | Connection issues, Incomplete data, Broken data tags, XML logs with incomplete parameters | Done
8 | Error conditions, clearing errors from App- additional commands between App and SCU | In progress
9 | Commands to quickly send joint id, user name, updated parameters partially | In progress
10 | Warning to user log memory about 80% full. Create backup of logs before it overwrites. As well as command to be able to clear memory from App if neeeded | Done testing with application is pending
11 | Remove firmware version from start record | Pending
12 | Start record should just give us Date, Time,Job Name,Joint Id,type of equipment,pipe diameter,logging distance (frequency of Logs taken)Supervisor,type of log. | Pending
13 | Adding logging distance during spray,pipe diameter. | Pending
14 | Sequence of records should be 1) Start Record 2) Version Record 3)Measurement Record 4) End Record | Pending